## Sheet 1
a | b | c | d | e | f | g | h | i | j | k | l
Status | meetingType | Title | Purpose | Facilitator | Recorder | Venue | Date | startTime | endTime | Agenda | Attendees
1 | Sprint Meet | meeting_domo_101 | ab | sajus | sajus | CT1-2-6284 | 06/02/2017 | 12:00:00 | 01:00:00 | abcdefghijkl | Saju Sasidharan,Pranav Kishore,Sagar Gaikwad
Discussion Points
discussionBy | discussionType | discussion | decisionBy | decision
vikasja | discussion | Vikas updated the status on DOMO-94394,DOMO-93705,DOMO-93726,DOMO-94278 | sandeepnab
vikasja | discussion | Josh discussed the tasks he is working on | vikasja
sandeepnab | discussion | Cybage team discussed their future leave plans | sajus
sandeepnab | discussion | Sandhya asked queries on observation found during testing, Josh clarified those | sajus
Action Points
actionDesc | responsible | openSince | expectedCompletion | actualCompletion | status
Josh to review PR #6893, 6895,6896, 6923 | sandeepnab | 08/02/2017 | 10/02/2017
Josh to check with Brandon for DOMO-92119, to comment on it (whether to display buzz icon or not) | vikasja | 08/02/2017 | 09/02/2017
Josh to ask Brandon to provide more details for DOMO-93084, as it is not reproducible at Cybage' end | sajus | 08/02/2017 | 14/02/2017
Vikas asked if we could have one default component to display in case of any broken image like in case of datasets , buzz message avatar pic, Josh to discuss same with Brandon | vikasja | 08/02/2017 | 09/02/2017