## Sheet 1
a | b | c | d | e | f | g | h | i | j | k | l
Status | meetingType | Title | Purpose | Facilitator | Recorder | Venue | Date | startTime | endTime | Agenda | Attendees
1 | Stand Up | DOMO_MoM_3 | undefined | Sandeep | Pranav | CT-2-8268 | 02-02-2017 | 11:30:00 | 12:00:00 | DOMO-112523 Advanced Notebook card:IE10- Can not upload an image through "Upload an Image" link DOMO-112342 Notebook Card: IE10-Color picker pop-up is not displayed. DOMO-112335 Incorrect image icon is not displaying | Sandeep Nabar, Sandeep Nabar, Sandeep Nabar, Sandeep Nabar, Sandeep Nabar, Sandeep Nabar, Sandeep Nabar, Sandeep Nabar, Sandeep Nabar, Sandeep Nabar
Discussion Points
discussionBy | discussionType | discussion | decisionBy | decision
Ravikumar | query | DOMO13789 card issue | Sandeep | updated that we will go ahead and create the card for DOMO13789.
Saju | discussion | discussed on DP17. | Sandeep | updated that we will go ahead and create the card for DP17.
Action Points
actionDesc | responsible | openSince | expectedCompletion | actualCompletion | status
Pendo improvements | Pravin | 23-01-2017 | 30-01-2017 | 06-04-2017 | Closed
NoteBook card tooltip issue | Ravikumar | 04-01-2017 | 26-01-2017 |  | In Progress