## Sheet 1
a | b | c | d | e | f | g | h | i | j | k | l
Status | meetingType | Title | Purpose | Facilitator | Recorder | Venue | Date | startTime | endTime | Agenda | Attendees
1 | Other | DOMO_MoM_1 | undefined | Sandeep | Durgesh | CT1-2-6284 | 06-04-2017 | 04:00:00 | 05:00:00 | 1) Demo 2) Suggestions | Sandeep Nabar, Sandeep Nabar, Sandeep Nabar, Sandeep Nabar
Discussion Points
discussionBy | discussionType | discussion | decisionBy | decision
Sandeep | discussion | Discussion on Meeting List Page | Sandeep | Change the Size of Glyphicons
Vikas | discussion | Discussion on Create New Meeting Page | Vikas | Keep the important fields in the left Panel of the form
Action Points
actionDesc | responsible | openSince | expectedCompletion | actualCompletion | status
Change the Size of Glyphicons | Sandeep | 06-04-2017 | 10-04-2017 |  | Open
Chenge the layout of the Create new Meeting Form | Vikas | 06-04-2017 | 07-04-2017 |  | In Progress