## Sheet 1
a | b | c | d | e | f | g | h | i | j | k | l
Status | meetingType | Title | Purpose | Facilitator | Recorder | Venue | Date | startTime | endTime | Agenda | Attendees
1 | Stand Up | DOMO_MoM_4 | undefined | Saju | Rupesh | CT-2-8269 | 24-03-2017 | 04:00:00 | 05:00:00 | DOMO-111757 Heading reset to default body font size when I apply UL/OL DOMO-105636 Text color loss when we apply UL/OL DOMO-99901 Apply/cancel bulleted list inside empty table changes table position in editor | Saju Sasidharan, Saju Sasidharan, Saju Sasidharan, Saju Sasidharan, Saju Sasidharan, Saju Sasidharan, Saju Sasidharan, Saju Sasidharan, Saju Sasidharan
Discussion Points
discussionBy | discussionType | discussion | decisionBy | decision
Durgesh | discussion | Issues with Medium Editor Library marked as Prep | Vikas | Can not upload an image through "Upload an Image" link
Saju | demo | Issues of Data Linage | Sandeep | appreciate work done on Data Linage.
Action Points
actionDesc | responsible | openSince | expectedCompletion | actualCompletion | status
Apply/cancel bulleted list inside empty table changes table position in editor | Pravin | 02-03-2017 | 14-04-2017 | 06-04-2017 | Closed