## Sheet 1
a | b | c | d | e | f | g | h | i | j | k | l
Status | meetingType | Title | Purpose | Facilitator | Recorder | Venue | Date | startTime | endTime | Agenda | Attendees
1 | Sprint Meet | meeting_domo_101 | Weekly Sprint Status meeting | Saju | Saju | CT1-2-6284 | 06-02-2017 | 12:00:00 | 01:00:00 | General Engineering updates,JIRA User Stories Status | Saju Sasidharan, Saju Sasidharan, Saju Sasidharan
Discussion Points
discussionBy | discussionType | discussion | decisionBy | decision
Vikas | discussion | Vikas updated the status on DOMO-94394,DOMO-93705,DOMO-93726,DOMO-94278 | Saju | decision1
Vikas | discussion | Josh discussed the tasks he is working on | Saju | decision2
Saju | discussion | asdasdas | Vikas | asdasdasd
Sandeep | query | Cybage team discussed their future leave plans | Sandeep | decision3
Saju | demo | Sandhya asked queries on observation found during testing, Josh clarified those | Sandeep | decision4
Action Points
actionDesc | responsible | openSince | expectedCompletion | actualCompletion | status
Josh to review PR #6893, 6895,6896, 6923 | Sandeep | 08-02-2017 | 10-02-2017 |  | Open
Josh to check with Brandon for DOMO-92119, to comment on it (whether to display buzz icon or not) | Vikas | 08-02-2017 | 09-02-2017 |  | Open
Josh to ask Brandon to provide more details for DOMO-93084, as it is not reproducible at Cybage' end | Saju | 08-02-2017 | 14-02-2017 |  | In Progress
Vikas asked if we could have one default component to display in case of any broken image like in case of datasets , buzz message avatar pic, Josh to discuss same with Brandon | Vikas | 08-02-2017 | 09-02-2017 |  | Closed
Descussion | Vikas | 30-03-2017 | 24-03-2017 | 20-03-2017 | Closed